## Sheet1
|  | 清潔費 | steve | Bill Shen | City fee | loan
買地 | 535000 | 600 | 3500 | 2000 | 3116 | 2206.85 | 546422.85
escrow | 17536.73 | 200 |  | 5700 |  | 2206.85 | 25643.58
notary | 90 | 600 |  | 6950 | 133 | 2206.85 | 9979.85
Gate | 3400 | 150 |  |  |  | 2206.85 | 5756.85
土壤report | 4200 |  |  |  |  | 2206.85 | 6406.85
Grading plans Structural Wall/calcs LID Report |  |  |  |  | 11001 | 2206.85 | 13207.85
[6 empty] | 2206.85 | 2206.85
[6 empty] | 2206.85 | 2206.85
| 560226.73 | 1550 | 3500 | 14650 | 14250 | 17654.8 | 611831.53
Note on B4: Mei: 3/1/2019
Note on B5: Mei: 2/27/2019
Note on C2: Mei: 12/15/2018
Note on C3: Mei: 2/27/2019
Note on C4: Mei: 4/1/2019
Note on D1: Mei: 47000
Note on E1: Mei: 25150
Note on E4: Mei: 5/2/2019
Note on F2: Mei: 2/27/2019
Note on F4: Mei: INSPECTION FEE
Note on F7: Mei: 5/8/2019
Note on G1: Mei: 219000
Note on G2: Mei: 2018-10
Note on G9: Mei: 2019-05

## Sheet2
project | date | completed | status
topo and boundary survey | 2019-02-14 | x | done
final map/loop calculation | 2019-02-14 | x | under city review
extension of map and CUP | 2019-03-07 | x | approved
radius map | 2019-03-07 | x | approved
grading plan | 2019-04-17 | x | under city review
erosion control plan | 2019-04-17 | x | under city review
hydrology report | 2019-04-17 | x | under city review
LID/BMP Report | 2019-04-17 | x | under city review