## cost
|  | 清潔費 | steve | Bill Shen | City fee | loan
買地 | 535000 | 600 | 3500 | 2000 | 3116 | 2206.85 | 546422.85
escrow | 17536.73 | 200 |  | 5700 |  | 2206.85 | 25643.58
notary | 90 | 600 |  | 6950 | 133 | 2206.85 | 9979.85
Gate | 3400 | 150 |  |  |  | 2206.85 | 5756.85
土壤report | 4200 |  |  |  |  | 2206.85 | 6406.85
Grading plans Structural Wall/calcs LID Report |  |  |  |  | 11001 | 2206.85 | 13207.85
[6 empty] | 2206.85 | 2206.85
| 560226.73 | 1550 | 3500 | 14650 | 14250 | 15447.95 | 609624.68
|  |  | 43500 | 10500 |  |  | 54000
project | date | completed | status |  |  |  | 663624.68
topo and boundary survey | 2019-02-14 | x | done
final map/loop calculation | 2019-02-14 | x | under city review
extension of map and CUP | 2019-03-07 | x | approved
radius map | 2019-03-07 | x | approved
grading plan | 2019-04-17 | x | under city review
erosion control plan | 2019-04-17 | x | under city review
hydrology report | 2019-04-17 | x | under city review
LID/BMP Report | 2019-04-17 | x | under city review
Note on B4: Mei: 3/1/2019
Note on B5: Mei: 2/27/2019
Note on C2: Mei: 12/15/2018
Note on C3: Mei: 2/27/2019
Note on C4: Mei: 4/1/2019
Note on D1: Mei: 47000
Note on E1: Mei: 25150
Note on E4: Mei: 5/2/2019
Note on F2: Mei: 2/27/2019
Note on F4: Mei: INSPECTION FEE
Note on F7: Mei: 5/8/2019
Note on G1: Mei: 219000
Note on G2: Mei: 2018-10
Note on G8: Mei: 2019-05

## Asset
Net-Value | 1989843.15 | 1250000 | 1250000 | Unit | LH-SF | PM-4 | PM-3 | WH-4 | WH-2 | E | D | C | B | A | 506 | 504 | 508 | 2Shop | Ref-Shop | Ref-487
Sum-Asset | 5127923.15 | 2645000 | 2645000 | $rent/mon | 3300 |  |  | 3650 | 4085.8333 | 5000 | 5000 | 5000 | 5200 | 5200 | 900 | 1800 | 2300 | 4100 | 2115 | 1900
Sum-Loan | 3138080 | 1395000 | 1395000 | lot | 6750 | 4791.6 | 4791.6 | 8906 | 9147.6 | 6969.6 | 6969.6 | 6969.6 | 6969.6 | 6969.6 | 800 | 857 | 1100 | 1957 | 900 | 1150
$net/mon | -2673.0809 | -664.2083 | -1163.375 | sqft | 2500 | 4284 | 2970 | 3910 | 2400 | 2757 | 2757 | 2757 | 2757 | 2757 | 1.125 | 2.1004 | 2.0909 | 2.095 | 2.35 | 1.6522
482 | 1150000 | 1150000 | 1150000 | $rent/ft | 1.32 | 0 | 0 | 0.9335 | 1.7024 | 1.8136 | 1.8136 | 1.8136 | 1.8861 | 1.8861 | 162900 | 325800 | 416300 | 742100 | 400000 | 500000
Compton-Land |  | 535000 | 535000 | $sale | 400000 | 599000 | 525000 | 595000 | 799000 | 880000 | 905000 | 905000 | 949000 | 949000 | 203.625 | 380.1634 | 378.4545 | 379.2029 | 444.4444 | 434.7826
Compton-Paid |  | 60000 | 60000 | $sale/ft | 160 | 139.8226 | 176.7677 | 152.1739 | 332.9167 | 319.1875 | 328.2554 | 328.2554 | 344.2147 | 344.2147 | 6.63% | 6.63% | 6.63% | 6.63% | 6.345% | 4.56%
Compton-Market | 3077923.15 |  |  | %rent/year | 9.9% | 0% | 0% | 7.361% | 6.136% | 6.818% | 6.63% | 6.63% | 6.575% | 6.575%
Shop | 900000 | 900000 | 900000 | cash-482 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000
Loan-482 | 625000 | 625000 | 625000 | cash-HM | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000
Loan-482-2 | 110000 |  |  | cash-SC | [7 empty] | 180000 |  | 180000 | 67 | 16.4% | 77.988
HardMoney | 220000 | 120000 | 220000 | laon | 20000 | 219000 | 145000 | 215000 | 419000 | 500000 | 525000 | 345000 | 569000 | 389000 | 74 | 15% | 85.1
Loan-SC |  | 100000 |  | Fee | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 2018-09-18 | 2018-11-02 | 9/18/2018 open escrow will close after 45 days
Loan-build | 1633080 |  |  | %482 | 5.63% | 5.63% | 5.63% | 5.63% | 5.63% | 5.63% | 5.63% | 5.63% | 5.63% | 5.63%
Loan-Shop | 550000 | 550000 | 550000 | %HM | 11.99% | 11.99% | 11.99% | 11.99% | 11.99% | 11.99% | 11.99% | 11.99% | 11.99% | 11.99%
ast/net | 2.577 | 2.116 | 2.116 | %SC | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5%
%loan/ast | 61.2% | 52.74% | 52.74% | %laon | 7.99% | 7.99% | 7.99% | 7.99% | 7.99% | 7.99% | 7.99% | 7.99% | 6.99% | 6.99%
%482 | 5.63% | 5.63% | 5.63% | $482/mon | 656.8333 | 656.8333 | 656.8333 | 656.8333 | 656.8333 | 656.8333 | 656.8333 | 656.8333 | 656.8333 | 656.8333
%482-2 | 12% | 5.63% | 5.63% | $HM/mon | 2248.125 | 2248.125 | 2248.125 | 2248.125 | 2248.125 | 2248.125 | 2248.125 | 2248.125 | 2248.125 | 2248.125
%HM | 11.99% | 11.99% | 11.99% | $SC/mon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 750
%SC | 6% | 6% | 6% | $laon/mon | 133.1667 | 1458.175 | 965.4583 | 1431.5417 | 2789.8417 | 3329.1667 | 3495.625 | 2297.125 | 3314.425 | 2265.925
%build | 10% | 10% | 10% | $int/mon | 3038.125 | 4363.1333 | 3870.4167 | 4336.5 | 5694.8 | 6234.125 | 6400.5833 | 5952.0833 | 6219.3833 | 5920.8833
%Shop | 7.49% | 7.49% | 7.49%
$482/mon | 2932.2917 | 2932.2917 | 2932.2917
$482-2/mon | 1100
$HM/mon | 2198.1667 | 1199 | 2198.1667
$SC/mon |  | 500
$build/mon | 13609
$Shop/mon | 3432.9167 | 3432.9167 | 3432.9167
$tt-inst/mon | 23272.375 | 8064.2083 | 8563.375
$482-rent | 2200 | 2200 | 2200
$condo-rent | 13199.2941
$Shop-rent | 5200 | 5200 | 5200
$tt-rent/mon | 20599.2941 | 7400 | 7400
%482-rent | 9.183% | 9.183% | 9.183%
%condo-rent | 5.146% | 0% | 0%
%Shop-rent | 6.933% | 6.933% | 6.933%
%tt-rent/mon | 5.795% | 4.982% | 4.982%
Note on G1: 551 W Whittier BlvdLa Habra, CA 90631 553 W Whittier BlvdLa Habra, CA 90631
Note on G4: 2 story
Note on H3: Lot: 0.11 Acres
Note on H4: 2 story
Note on I3: Lot: 0.11 Acres
Note on J1: 7316 Painter Ave, Whittier, CA 90602
Note on J3: Lot: 0.31 Acres 13504 sf ??
Note on K3: Lot: 0.21 Acres 9150 sf
Note on L3: Lot: 0.16 Acres 6970 sf
Note on M3: Lot: 0.16 Acres 6970 sf
Note on N3: Lot: 0.16 Acres 6970 sf
Note on O3: Lot: 0.16 Acres 6970 sf
Note on P3: Lot: 0.16 Acres 6970 sf

## H5
| 20190617 | 20190501 | 20190304 | Bellflower | Norwalk | Whittier | Buena Park | Whitier | Corona
| 6連排 | 6連排 | 6連排 | 1大棟 | 5連排2.5浴 | 3二層 | 3Condo | T型地 | 6-7公寓
sq.ft | 21779.5 | 21779.5 | 21779.5 | 8677 | 11760.93 | 20037.14 | 6751 | 49657.26 | 14810.06 | 3484.72
units | 6 | 6 | 6 | 3 | 5 | 3 | 3 | 11 | 6 | 0.036256
$-lots | 535000 | 535000 | 535000 | 599999 | 757000 | 745000 | 850000 | 895000 | 399000
$-lot/unit | 89166.6667 | 89166.6667 | 89166.6667 | 199999.6667 | 151400 | 248333.3333 | 283333.3333 | 81363.6364 | 66500
$-design | 80000 | 80000 | 50000
$-design/unit | 13333.3333 | 13333.3333 | 8333.3333 | 0 | 0 | 0 | 0 | 0 | 0
$-land
$-land/unit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
$-permit | 70000 | 70000 | 50000
$-permit/unit | 11666.6667 | 11666.6667 | 8333.3333 | 0 | 0 | 0 | 0 | 0 | 0
$-sub cost/unit | 114166.6667 | 114166.6667 | 105833.3333 | 199999.6667 | 151400 | 248333.3333 | 283333.3333 | 81363.6364 | 66500
house ft | 1626 | 1626 | 1626 | 1550.3333 | 1350 | 2700 | 3299.3333 | 1600 | 1135
$-house/ft | 150 | 150 | 130 | 130 | 130 | 130 | 130 | 130 | 130
park ft | 404 | 404 | 404 | 426 | 440 | 440 | 440 | 440 | 440
$-park/ft | 70 | 70 | 60 | 60 | 60 | 60 | 60 | 60 | 60
$-built/unit | 272180 | 272180 | 235620 | 227103.3333 | 201900 | 377400 | 455313.3333 | 234400 | 173950
$-cost/unit | 386346.6667 | 386346.6667 | 341453.3333 | 427103 | 353300 | 625733.3333 | 738646.6667 | 315763.6364 | 240450
$-built tt | 1633080 | 1633080 | 1413720 | 681310 | 1009500 | 1132200 | 1365940 | 2578400 | 1043700
$-built/ft | 167.3924 | 167.3924 | 144.9077 | 146.4868 | 149.5556 | 139.7778 | 138.0016 | 146.5 | 153.2599
$-cost tt | 2318080 | 2318080 | 2048720 | 1281309 | 1766500 | 1877200 | 2215940 | 3473400 | 1442700
$-cost/ft | 237.6056 | 237.6056 | 209.9959 | 275.4911 | 261.7037 | 231.7531 | 223.8776 | 197.3523 | 211.8502
10% | 429274.0741 | 429274.0741 | 379392.5926 | 474558.8889 | 392555.5556 | 695259.2593 | 820718.5185 | 350848.4848 | 267166.6667
15% | 454525.4902 | 454525.4902 | 401709.8039 | 502474.1176 | 415647.0588 | 736156.8627 | 868996.0784 | 371486.631 | 282882.3529
20% | 482933.3333 | 482933.3333 | 426816.6667 | 533878.75 | 441625 | 782166.6667 | 923308.3333 | 394704.5455 | 300562.5
25% | 515128.8889 | 515128.8889 | 455271.1111 | 569470.6667 | 471066.6667 | 834311.1111 | 984862.2222 | 421018.1818 | 320600
30% | 551923.8095 | 551923.8095 | 487790.4762 | 610147.1429 | 504714.2857 | 893904.7619 | 1055209.5238 | 451090.9091 | 343500
35% | 594379.4872 | 594379.4872 | 525312.8205 | 657081.5385 | 543538.4615 | 962666.6667 | 1136379.4872 | 485790.2098 | 369923.0769
$-market/unit | 512987.1917 | 458248.4662 | 419550.9083 | 494914.1026 | 415565.2174 | 779181.2343 | 415565.2174 | 520000 | 270000
land/market | 22.26% | 24.91% | 25.23% | 40.41% | 36.43% | 31.87% | 68.18% | 15.65% | 24.63%
cost/market | 75.31% | 84.31% | 81.39% | 86.3% | 85.02% | 80.31% | 177.7% | 60.72% | 89.06%
$-rent/mon | 2199.8824 | 2199.8824 | 2199.8824 | 2742.8974 | 2300 | 3957.6547 | 2300 | 2500 | 1625
rent% | 6.833% | 6.833% | 7.731% | 7.707% | 7.812% | 7.59% | 3.737% | 9.501% | 8.11%
tt house ft | 9756 | 9756 | 9756 | 4651 | 6750 | 8100 | 9898 | 17600 | 6810
$-market/ft | 315.4903 | 281.8256 | 258.0264 | 319.2308 | 307.8261 | 288.5856 | 125.9543 | 325 | 237.8855
$-zip-ref/ft | 270 | 270 | 270 | 350 | 390 | 385 | 390 | 385 | 260
| 445 | 445
| 146 | 146
| 3.0479 | 3.0479
Note on C1: 809 E Pine St, Compton, CA 90221
Note on C2: DATE EVENT PRICE AGENTS 8/30/2018 Sold $535,000 -- zuser20170313231855204 7/28/2018 Price change $535,000 -7% 7/26/2018 Price change $575,000 -8% 7/19/2018 Listed for sale $625,000 +2.6% 6/7/2018 Listing removed $609,000 -- 5/23/2018 Price change $609,000 -9% 5/17/2018 Price change $669,000 -2.3% 5/4/2018 Price change $685,000 -8.1% 4/25/2018 Price change $745,000 -6.3% 4/17/2018 Listed for sale $795,000 +14.4% 1/10/2018 Listing removed $695,000 -- 10/12/2017 Price change $695,000 -12.6% 10/4/2017 Listed for sale $795,000 +148.4% 3/21/2014 Sold $320,000 -8.6% 7/3/2011 Listing removed $350,000 -5.4% 2/6/2008 Sold $370,000 -39.9% 8/28/2007 Sold $615,343 +107.1% 10/10/2003 Sold $297,118 -- 11/4/2002 Sold $297,118 +6.9% 8/20/2001 Sold $278,000 +68.5% 11/16/1999 Sold $165,000 +10.6% 8/13/1999 Sold $149,130 --
Note on C3: 0.5 acres
Note on C4: max 30 units/acre 0.43 x 30 = 12.89
Note on C5: 20180727 575000 -> 535000 20180725 625000 -> 575000 20180722 relist -> 625000 THIS IS A LAND DEAL ONLY. SELLER WILL PROVIDE THE FOLLOWING ONLY ! :1-Architectural Design 2-Structural plans 3-Electrical plans 4-Mechanical and Plumbing plans 5-Title24 6 Grading Plan 7-Tentative tract map 8-Landscaping 9-Color Rendering and material & color Board 10-Conditional Approval from planning 11-Conditional Approval from planning for Subdivision PERIOD...... NOTHING MORE. BUYER TO DO THEIR OWN INVESTIGATIONS. MAKE SURE YOU ARE COMFORTABLE WITH COMPTON 20180615 609000 -> 680000
Note on C7: 20190501 50000->80000
Note on C11: 20190501 50000->70000
Note on C16: double 20 x 22
Note on C17: ref 28465/560
Note on C18: 吳老闆最近承接ㄌrevirside 96 unit apart 總造價１２００萬美金 1200/96=12.5
Note on C20: You Will Need to Put Down a Large Down Payment. Typically, 20% is the minimum you need to put down for a construction loan – some lenders require as much as 25% down.
Note on C30: 812 E Pine St UNIT C Compton, CA 90221 1440 sft 20180725 340000->358657 20190116 ->369534 20190206 ->371558 20190501 ->452813 20190528 ->449359 20190617 ->450921 20190630 ->454306
Note on C33: 812 E Pine St UNIT A, Compton, CA 90221 1700ft
Note on D1: 809 E Pine St, Compton, CA 90221
Note on D2: DATE EVENT PRICE AGENTS 8/30/2018 Sold $535,000 -- zuser20170313231855204 7/28/2018 Price change $535,000 -7% 7/26/2018 Price change $575,000 -8% 7/19/2018 Listed for sale $625,000 +2.6% 6/7/2018 Listing removed $609,000 -- 5/23/2018 Price change $609,000 -9% 5/17/2018 Price change $669,000 -2.3% 5/4/2018 Price change $685,000 -8.1% 4/25/2018 Price change $745,000 -6.3% 4/17/2018 Listed for sale $795,000 +14.4% 1/10/2018 Listing removed $695,000 -- 10/12/2017 Price change $695,000 -12.6% 10/4/2017 Listed for sale $795,000 +148.4% 3/21/2014 Sold $320,000 -8.6% 7/3/2011 Listing removed $350,000 -5.4% 2/6/2008 Sold $370,000 -39.9% 8/28/2007 Sold $615,343 +107.1% 10/10/2003 Sold $297,118 -- 11/4/2002 Sold $297,118 +6.9% 8/20/2001 Sold $278,000 +68.5% 11/16/1999 Sold $165,000 +10.6% 8/13/1999 Sold $149,130 --
Note on D3: 0.5 acres
Note on D4: max 30 units/acre 0.43 x 30 = 12.89
Note on D5: 20180727 575000 -> 535000 20180725 625000 -> 575000 20180722 relist -> 625000 THIS IS A LAND DEAL ONLY. SELLER WILL PROVIDE THE FOLLOWING ONLY ! :1-Architectural Design 2-Structural plans 3-Electrical plans 4-Mechanical and Plumbing plans 5-Title24 6 Grading Plan 7-Tentative tract map 8-Landscaping 9-Color Rendering and material & color Board 10-Conditional Approval from planning 11-Conditional Approval from planning for Subdivision PERIOD...... NOTHING MORE. BUYER TO DO THEIR OWN INVESTIGATIONS. MAKE SURE YOU ARE COMFORTABLE WITH COMPTON 20180615 609000 -> 680000
Note on D7: 20190501 50000->80000
Note on D11: 20190501 50000->70000
Note on D16: double 20 x 22
Note on D17: ref 28465/560
Note on D18: 吳老闆最近承接ㄌrevirside 96 unit apart 總造價１２００萬美金 1200/96=12.5
Note on D20: You Will Need to Put Down a Large Down Payment. Typically, 20% is the minimum you need to put down for a construction loan – some lenders require as much as 25% down.
Note on D30: 812 E Pine St UNIT C Compton, CA 90221 1440 sft 20180725 340000->358657 20190116 ->369534 20190206 ->371558 20190501 ->452813 20190528 ->449359 20190617 ->450921
Note on D33: 812 E Pine St UNIT A, Compton, CA 90221 1700ft
Note on E1: 809 E Pine St, Compton, CA 90221
Note on E3: 0.5 acres
Note on E5: 20180727 575000 -> 535000 20180725 625000 -> 575000 20180615 609000 -> 680000 20180722 relist -> 625000 THIS IS A LAND DEAL ONLY. SELLER WILL PROVIDE THE FOLLOWING ONLY ! :1-Architectural Design 2-Structural plans 3-Electrical plans 4-Mechanical and Plumbing plans 5-Title24 6 Grading Plan 7-Tentative tract map 8-Landscaping 9-Color Rendering and material & color Board 10-Conditional Approval from planning 11-Conditional Approval from planning for Subdivision PERIOD...... NOTHING MORE. BUYER TO DO THEIR OWN INVESTIGATIONS. MAKE SURE YOU ARE COMFORTABLE WITH COMPTON
Note on E30: 812 E Pine St UNIT C Compton, CA 90221 20180725 340000->358657 20190116 ->369534 20190206 ->371558
Note on E33: 812 E Pine St UNIT A, Compton, CA 90221 1700ft
Note on G1: 8524 Park St, Bellflower, CA 90706
Note on G14: A: 605+708=1313 B: 858+950=1808 C: 818+712=1530
Note on G30: 8527-8545 Park St, Bellflower, CA 90706
Note on H1: 12025 Orange St, Norwalk, CA 90650
Note on H3: 0.27 acres
Note on H30: 12007 Orange St, Norwalk, CA 90650
Note on J1: 14260 Keese Dr, Whittier, CA 90604
Note on J3: 0.46 acres
Note on J30: 12130 Valley View Ave, Whittier, CA 90604
Note on K1: 5801 Homewood Ave, Buena Park, CA 90621
Note on K14: Unit 1, 3456 sq ft 4 Bedrooms & 3.5 Baths Unit 2, 3182 sq ft 4 Bedrooms & 3 Baths Unit 3, 3258 sq ft 4 Bedrooms & 3 Baths
Note on K30: 12007 Orange St, Norwalk, CA 90650
Note on L1: 10123 Lanett Ave, Whittier, CA 90605
Note on L3: 1.14 acres
Note on M1: 1109 Circle City Dr, Corona, CA 92879
Note on M3: 0.34 acres
Note on M30: 983 Elsa Ct Unit B, Corona, CA 92881
Note on N3: 0.5 acres

## H6
-80% | H6 | 800000 | 5.484% | -3656.25
36.5% | 480-L | -365000 | 5.625% | -1710.9375
-0% | HM |  | 11.99% | 0
20% | SC | -200000 | 5% | -833.3333
-2% | SC-Shop | 20000 | 5% | 83.3333
25.5% | H6-L | -255000 | 5.625% | -1195.3125
-80% | H6 | 800000 | 3.734% | -2489.3333
36.5% | 480-L | -365000 | 5.625% | -1710.9375
-22% | HM | 220000 | 11.99% | 2198.1667
20% | SC | -200000 | 5% | -833.3333
-2% | SC-Shop | 20000 | 5% | 83.3333
47.5% | H6-L | -475000 | 5.625% | -2226.5625
-100% | H6 | 1000000 | 5.513% | -4593.75
36.5% | 480-L | -365000 | 5.625% | -1710.9375
-0% | HM |  | 11.99% | 0
20% | SC | -200000 | 5% | -833.3333
-2% | SC-Shop | 20000 | 5% | 83.3333
45.5% | H6-L | -455000 | 5.625% | -2132.8125
-100% | H6 | 1000000 | 4.112% | -3426.8333
36.5% | 480-L | -365000 | 5.625% | -1710.9375
-22% | HM | 220000 | 11.99% | 2198.1667
20% | SC | -200000 | 5% | -833.3333
-2% | SC-Shop | 20000 | 5% | 83.3333
67.5% | H6-L | -675000 | 5.625% | -3164.0625

## Loan
| Hard Money |  | 480 Loan 50% | 480 Loan 60% |  | 1-借現金
487售出 | 310000 |  | 310000 | 310000 |  | 2-銀行保證轉錢
Buy Land | -535000 |  | -535000 | -535000 |  | 3-Escrow close延期
SC-Cash | 40000 |  | 40000 | 40000 |  | 4-HM 拒絕
HM-Loan | 250000 | 480估值 | 950000 | 950000 |  | 5-賭HM最後期限之前
HM-point% | -4% | 480貸% | 50% | 60%
HM-point | -10000 | 480轉貸 | 475000 | 570000
HM-利率% | -11.99% | 480還貸 | -240000 | -240000
HM-fee | -3580 | 480-fee | -10000 | -10000
1031/land-fee | -10000 | Cash Out | 225000 | 320000
買地餘額 | 41420 |  | 40000 | 135000
建屋 | -1633080 |  | -1633080 | -1633080
建成單價 | 512987.1917 |  | 512987.1917 | 512987.1917
Unit | 6 |  | 6 | 6
建成估值 | 3077923.15 |  | 3077923.15 | 3077923.15
建築貸款利率% | 65% |  | 65% | 65%
建築貸款 | 2000650.0475 |  | 2000650.0475 | 2000650.0475
建築餘額 | 367570.0475 |  | 367570.0475 | 367570.0475
合計餘額 | 408990.0475 |  | 407570.0475 | 502570.0475
借半年 | Loan | point | amount | agent% | amount | intest% | amount | sunmmary | 差額 | 月利息
Hard Money
480-loan-old | 240000 |  | 0 |  | 0 | 5% | 6000 | 6000 |  | 1000
SC | 40000 |  | 0 |  | 0 | 5% | 1000 | 1000 |  | 166.6667
Land loan(HM) | 250000 | 3% | 7500 | 1% | 2500 | 11.99% | 14987.5 | 24987.5 |  | 2497.9167
total | 530000 |  | 7500 |  | 2500 |  | 21987.5 | 31987.5 |  | 3664.5833
480 Loan 50%
480-loan-new | 475000 | 1% | 4750 | 1% | 4750 | 5.625% | 13359.375 | 22859.375 |  | 2226.5625
SC | 40000 |  | 0 |  | 0 | 5% | 1000 | 1000 |  | 166.6667
total | 515000 |  | 4750 |  | 4750 |  | 14359.375 | 23859.375 | -8128.125 | 2393.2292 | -1271.3542
480 Loan 60%
480-loan-new | 570000 | 1% | 5700 | 1% | 5700 | 5.625% | 16031.25 | 27431.25 |  | 2671.875
SC | 40000 |  | 0 |  | 0 | 5% | 1000 | 1000 |  | 166.6667
total | 610000 |  | 5700 |  | 5700 |  | 17031.25 | 28431.25 | -3556.25 | 2838.5417 | -826.0417
借一年 | Loan | point | amount | agent% | amount | intest% | amount | sunmmary | 差額 | 月利息
Hard Money
480-loan-old | 240000 |  | 0 |  | 0 | 5% | 12000 | 12000 |  | 1000
SC | 40000 |  | 0 |  | 0 | 5% | 2000 | 2000 |  | 166.6667
Land loan(HM) | 250000 | 3% | 7500 | 1% | 2500 | 11.99% | 29975 | 39975 |  | 2497.9167
total | 530000 |  | 7500 |  | 2500 |  | 43975 | 53975 |  | 3664.5833
480 Loan 50%
480-loan-new | 475000 | 2% | 9500 | 1% | 4750 | 5.625% | 26718.75 | 40968.75 |  | 2226.5625
SC | 40000 |  | 0 |  | 0 | 5% | 2000 | 2000 |  | 166.6667
total | 515000 |  | 9500 |  | 4750 |  | 28718.75 | 42968.75 | -11006.25 | 2393.2292
480 Loan 60%
480-loan-new | 570000 | 2% | 11400 | 1% | 5700 | 5.625% | 32062.5 | 49162.5 |  | 2671.875
SC | 40000 |  | 0 |  | 0 | 5% | 2000 | 2000 |  | 166.6667
total | 610000 |  | 11400 |  | 5700 |  | 34062.5 | 51162.5 | -2812.5 | 2838.5417
每個月 | Loan | intest% | amount | 差額
原利息支出
480-loan-old | 240000 | 5% | 1000
SC | 40000 | 5% | 166.6667
total | 280000 |  | 1166.6667
480 Loan 50%
480-loan-new | 475000 | 5.625% | 2226.5625
total | 475000 |  | 2226.5625 | -1059.8958
480 Loan 60%
480-loan-new | 570000 | 5.625% | 2671.875
total | 570000 |  | 2671.875 | -1505.2083

## ToDo
| Compton |  | Compton-0 | Bellflower | Norwalk | Whitier | CORONA
487售出 | 310000 |  | 310000 | 310000 | 310000 | 310000 | 310000
Buy Land | -535000 |  | -535000 | -599999 | -757000 | -895000 | -399000
SC-Cash | 40000 |  | 40000 | 40000 | 40000 | 40000 | 40000
HM-Loan | 220000 | 480估值 | 1000000 | 950000 | 950000 | 950000 | 950000
HM-point% | -4% | 480貸% | 62.5% | 50% | 50% | 70% | 70%
HM-point | -8800 | 480轉貸 | 625000 | 475000 | 475000 | 665000 | 665000
HM-利率% | -11.99% | 480還貸 | -240000 | -240000 | -240000 | -240000 | -240000
HM-fee | -3580 | 480-fee | -10000 | -10000 | -10000 | -10000 | -10000
1031/land-fee | -10000 | Cash Out | 375000 | 535000 | 535000 | 725000 | 725000
餘額 | 12620 | 餘額 | 190000 | -24999 | -182000 | -130000 | 366000
建屋 | -1633080 |  | -1633080 | -681310 | -1009500 | -2578400 | -1043700
建成單價 | 512987.1917 |  | 512987.1917 | 494914.1026 | 415565.2174 | 520000 | 270000
Unit | 6 |  | 6 | 3 | 5 | 11 | 6
建成估值 | 3077923.15 |  | 3077923.15 | 1484742.3077 | 2077826.087 | 5720000 | 1620000
建貸% | 65% |  | 65% | 65% | 65% | 65% | 65%
建貸 | 2000650.0475 |  | 2000650.0475 | 965082.5 | 1350586.9565 | 3718000 | 1053000
餘額 | 367570.0475 |  | 367570.0475 | 283772.5 | 341086.9565 | 1139600 | 9300
總餘額 | 380190.0475 |  | 557570.0475 | 258773.5 | 159086.9565 | 1009600 | 375300
20180814 | 22127 Loan Approval
| Loan | point | amount | agent% | amount | intest% | amount | sunmmary
Hard Money | [11 empty] | 975
480-loan-now | 240000 |  | 0 |  | 0 | 5% | 12000 | 12000 |  |  |  | 655
SC | 40000 |  | 0 |  | 0 | 5% | 2000 | 2000 |  |  |  | 890
Land loan(HM) | 220000 | 3% | 6600 | 1% | 2200 | 11.99% | 26378 | 35178 |  |  |  | 585
total | 500000 |  | 6600 |  | 2200 |  | 40378 | 49178 | <--- first year |  | -478.25 | 45
480 Loan | [11 empty] | 35
480-loan-new | 625000 | 1% | 6250 | 1% | 6250 | 5.625% | 35156.25 | 47656.25 |  |  |  | 395
SC | 40000 |  | 0 |  | 0 | 5% | 2000 | 2000 |  |  |  | 3580
total | 665000 |  | 6250 |  | 6250 |  | 37156.25 | 49656.25 | <--- first year |  |  | 0.031667
480 Loan | [11 empty] | 35
480-loan-new | 750000 | 1% | 7500 | 1% | 7500 | 5.625% | 42187.5 | 57187.5 |  |  |  | 395
SC | 40000 |  | 0 |  | 0 | 5% | 2000 | 2000 |  |  |  | 4485.0317
total | 790000 |  | 7500 |  | 7500 |  | 44187.5 | 59187.5 | <--- first year |  |  | 0.031667
20180803 | 22127 Loan Approval
| Loan | % | point | amount | agent% | amount | intest% | amount | sunmmary
Compton | 535000
480-loan-now | 240000 |  |  | 0 |  | 0 | 5% | 12000 | 12000 |  |  |  | 975
487-1031 | 310000 | 51.67% |  | 0 |  | 0 |  | 0 | 0 |  |  |  | 655
SC | 40000 | 6.667% |  | 0 |  | 0 | 5% | 2000 | 2000 |  |  |  | 890
Land loan | 220000 | 36.67% | 3% | 6600 | 1% | 2200 | 11.99% | 26378 | 35178 |  |  |  | 585
total | 570000 | 95% |  | 6600 |  | 2200 |  | 40378 | 49178 | <--- first year |  | 228 | 45
480自住 | 550000 | [11 empty] | 35
1st | 475000 | 50% | 2% | 9500 | 1% | 4750 | 6% | 28500 | 42750 |  |  |  | 395
SC | 40000 | 4.211% |  | 0 |  | 0 | 5% | 2000 | 2000 |  |  |  | 3580
Hard Money | 30000 | 3.158% | 3% | 900 | 1% | 300 | 10% | 3000 | 4200
total | 545000 | 57.37% |  | 10400 |  | 5050 |  | 33500 | 48950 | <--- first year |  |  | 0.031667
20180729 | Compton land loan
| Loan | % | point | amount | agent% | amount | intest% | amount | sunmmary
Compton | 550000
480-loan-now | 240000 |  |  | 0 |  | 0 | 5% | 12000 | 12000
487-1031 | 310000 | 51.67% |  | 0 |  | 0 |  | 0 | 0
SC | 44000 | 7.333% |  | 0 |  | 0 | 5% | 2200 | 2200
Land loan | 196000 | 32.67% | 3% | 5880 | 1% | 1960 | 10% | 19600 | 27440
total | 550000 | 91.67% |  | 5880 |  | 1960 |  | 33800 | 41640 | <--- first year |  | -7510
480自住 | 550000
1st | 475000 | 50% | 2% | 9500 | 1% | 4750 | 6% | 28500 | 42750
SC | 44000 | 4.632% |  | 0 |  | 0 | 5% | 2200 | 2200
Hard Money | 30000 | 3.158% | 3% | 900 | 1% | 300 | 10% | 3000 | 4200
total | 549000 | 57.79% |  | 10400 |  | 5050 |  | 33700 | 49150 | <--- first year |  |  | 0.031667
20180616 | 如果要改買Comptonland loan application.
It is 50 LTV. Rate 10.5%, fee 3+1 point.
| Loan | % | point | amount | agent% | amount | intest% | amount | sunmmary
Compton | 680000
480-loan-now | 240000 |  |  | 0 |  | 0 | 5% | 12000 | 12000
487-1031 | 310000 | 51.67% |  | 0 |  | 0 |  | 0 | 0
SC | 44000 | 7.333% |  | 0 |  | 0 | 5% | 2200 | 2200
seller loan | 326000 | 54.33% | 3% | 9780 | 1% | 3260 | 10.05% | 32763 | 45803 |  |  | 8120.02
total | 680000 | 113.3% |  | 9780 |  | 3260 |  | 46963 | 60003 | <--- first year |  | 16283.12
480自住 | 680000
1st | 475000 | 50% | 2% | 9500 | 1% | 4750 | 6% | 28500 | 42750 |  |  | 204
SC | 44000 | 4.632% |  | 0 |  | 0 | 5% | 2200 | 2200
Hard Money | 161000 | 16.95% | 3% | 4830 | 1% | 1610 | 10% | 16100 | 22540
total | 680000 | 71.58% |  | 14330 |  | 6360 |  | 46800 | 67490 | <--- first year
[9 empty] | 23550 | <---只貸1st PSG差價
Bell flower seller will carry a Loan.
Rate is10%, fee is 2 point.
Bellflower | 599999
480-loan-now | 240000 |  |  | 0 |  | 0 | 5% | 12000 | 12000
487-1031 | 310000 | 51.67% |  | 0 |  | 0 |  | 0 | 0
SC | 44000 | 7.333% |  | 0 |  | 0 | 5% | 2200 | 2200
seller loan | 245999 | 41% | 2% | 4919.98 |  | 0 | 10% | 24599.9 | 29519.88
total | 599999 | 100% |  | 4919.98 |  | 0 |  | 38799.9 | 43719.88 | <--- first year
PSG
1st $540k, 8%, 4pt
2nd, $125k, 10.99%, 5pt.
Pre pay penalty 3 month.
Term 12-15 month.
| Loan | % | point | amount | agent% | amount | intest% | amount | sunmmary
PSG | 950000
1st | 540000 | 56.84% | 4% | 21600 | 1% | 5400 | 8% | 43200 | 70200
2nd | 125000 | 13.16% | 5% | 6250 | 1% | 1250 | 10.99% | 13737.5 | 21237.5
total | 665000 | 70% |  | 27850 |  | 6650 |  | 56937.5 | 91437.5 | <--- first year
Target | 950000
1st | 475000 | 50% | 2% | 9500 | 1% | 4750 | 6% | 28500 | 42750
2nd | 30000 | 3.158% | 2% | 600 | 1% | 300 | 10% | 3000 | 3900
SC | 44000 | 4.632% |  | 0 |  | 0 | 5% | 2200 | 2200
total | 549000 | 57.79% |  | 10100 |  | 5050 |  | 33700 | 48850 | <--- first year
[9 empty] | 42587.5 | <---全PSG差價
Note on B22: 20180731 Loan approved, But the rate is much higher than we quote before. Quote was from AE, he said land is higher than regular loan.
Note on B38: 20180731 Loan approved, But the rate is much higher than we quote before. Quote was from AE, he said land is higher than regular loan.
Note on B52: 20180729 We are brand new in investment business. No qualified tax return. We can only take hard money loan. 1, Need 30% down, 2, charge 4 point + fees 3, rate 9 -10 %. 4, term 3 years, 5, prepayment penalty 1 year. 6, escrow 10 -15 working days. Cotrection... Pre pay penalty is 6 month. Point - Lender 2 point, AAA 1 point JJ 1 point. Compton listing $535,000. 1, Lender ok with 6 month prepay penalty. 2, AAA still charge 1% fee, cause loan amount is $200,000 only. Compton 土地假如決定了, 請先寫個貸款申請表, 我們需要lender approval letter to submit offer. Lender suggested 3 weeks escrow.

## New
工業商用RO | 專用鋁架 | 輪具 | 不鏽鋼架 | 行動式拖架 | 定作款RO
專用RO | 洗車 | 大樓外牆 | RV | 降溫降塵
噴淋 | 滴灌 | 無土栽培 | 有機作物 | 水耕 | 水族
咖啡機 | 飲水機 | 冰箱制冰 | 洗衣機 | 沐浴龍頭 | 定作改裝
自吸水泵 | 遊艇 | 印刷機 | 電鍍機 | 超音波
廣告 | LED | 跑馬燈 | 監控系統 | 人工會慧視別系統
雹子煙 | 大麻 | 美容儀 | 補水機 | 無人機 | 雷射切斷車
包裝泡袋 | 泡袋機 | 出口濾芯 | 智慧冰櫃 | 機場接送APP
寵物用品開發,品牌,新產品設計,專櫃,貿易,寄賣,加盟,中國代購,美國代購
寵物濾芯,浮球,狗盆,給水器,衣物,裝飾品
上門溜狗,看狗,美容,買賣APP