## cost
|  | 清潔費 | steve | Bill Shen | City fee | loan | Sumary | project | date | completed | status
買地 | 535000 | 600 | 3500 | 2000 | 3116 | 2206.85 | 546422.85 | topo and boundary survey | 2019-02-14 | x | done
escrow | 17536.73 | 200 |  | 5700 |  | 2206.85 | 25643.58 | final map/loop calculation | 2019-02-14 | x | under city review
notary | 90 | 600 |  | 6950 | 133 | 2206.85 | 9979.85 | extension of map and CUP | 2019-03-07 | x | approved
Gate | 3400 | 150 |  |  |  | 2206.85 | 5756.85 | radius map | 2019-03-07 | x | approved
土壤report | 4200 |  |  |  |  | 2206.85 | 6406.85 | grading plan | 2019-04-17 | x | under city review
Grading plans Structural Wall/calcs LID Report |  |  |  |  | 11001 | 2206.85 | 13207.85 | erosion control plan | 2019-04-17 | x | under city review
[6 empty] | 2206.85 | 2206.85 | hydrology report | 2019-04-17 | x | under city review
sub-total | 560226.73 | 1550 | 3500 | 14650 | 14250 | 15447.95 | 609624.68 | LID/BMP Report | 2019-04-17 | x | under city review
Unpaid |  |  | 43500 | 10500 |  |  | 54000
[6 empty] | Total | 663624.68
Note on B4: Mei: 3/1/2019
Note on B5: Mei: 2/27/2019
Note on C2: Mei: 12/15/2018
Note on C3: Mei: 2/27/2019
Note on C4: Mei: 4/1/2019
Note on D1: Mei: 47000
Note on E1: Mei: 25150
Note on E4: Mei: 5/2/2019
Note on F2: Mei: 2/27/2019
Note on F4: Mei: INSPECTION FEE
Note on F7: Mei: 5/8/2019
Note on G1: Mei: 219000
Note on G2: Mei: 2018-10
Note on G8: Mei: 2019-05

## Asset
201905
Net-Value | 1966909.775 | 1250000 | 1250000
Sum-Asset | 5104989.775 | 2645000 | 2645000
Sum-Loan | 3138080 | 1395000 | 1395000
$net/mon | -2673.0809 | -664.2083 | -1163.375
482 | 1150000 | 1150000 | 1150000
Compton-Land |  | 535000 | 535000
Compton-Paid |  | 60000 | 60000
Compton-Market | 3054989.775
Shop | 900000 | 900000 | 900000
Loan-482 | 625000 | 625000 | 625000
Loan-482-2 | 110000
HardMoney | 220000 | 120000 | 220000
Loan-SC |  | 100000
Loan-build | 1633080 |  |  |  | 1633080 | 10%
Loan-Shop | 550000 | 550000 | 550000 | 10% | 163308 | 1360.9
ast/net | 2.5954 | 2.116 | 2.116 | 20% | 326616 | 2721.8
%loan/ast | 61.47% | 52.74% | 52.74% | 30% | 489924 | 4082.7
%482 | 5.63% | 5.63% | 5.63% | 40% | 653232 | 5443.6
%482-2 | 12% | 5.63% | 5.63% | 50% | 816540 | 6804.5
%HM | 11.99% | 11.99% | 11.99% | 60% | 979848 | 8165.4
%SC | 6% | 6% | 6% | 70% | 1143156 | 9526.3
%build | 10% | 10% | 10% | 80% | 1306464 | 10887.2
%Shop | 7.49% | 7.49% | 7.49% | 90% | 1469772 | 12248.1
$482/mon | 2932.2917 | 2932.2917 | 2932.2917 | 100% | 1633080 | 13609
$482-2/mon | 1100 |  |  |  |  | 74849.5 | 0.055
$HM/mon | 2198.1667 | 1199 | 2198.1667
$SC/mon |  | 500
$build/mon | 13609
$Shop/mon | 3432.9167 | 3432.9167 | 3432.9167
$tt-inst/mon | 23272.375 | 8064.2083 | 8563.375
$482-rent | 2200 | 2200 | 2200
$condo-rent | 13199.2941
$Shop-rent | 5200 | 5200 | 5200
$tt-rent/mon | 20599.2941 | 7400 | 7400
%482-rent | 9.183% | 9.183% | 9.183%
%condo-rent | 5.185% | 0% | 0%
%Shop-rent | 6.933% | 6.933% | 6.933%
%tt-rent/mon | 5.827% | 4.982% | 4.982%

## Compton
| 20191001 | 20190913 | 20190617 | 20190501 | 20190304
| 6連排 | 6連排 | 6連排 | 6連排 | 6連排
sq.ft | 21779.5 | 21779.5 | 21779.5 | 21779.5 | 21779.5
units | 6 | 6 | 6 | 6 | 6
$-lots | 535000 | 535000 | 535000 | 535000 | 535000
$-lot/unit | 89166.6667 | 89166.6667 | 89166.6667 | 89166.6667 | 89166.6667
$-design | 80000 | 80000 | 80000 | 80000 | 50000
$-design/unit | 13333.3333 | 13333.3333 | 13333.3333 | 13333.3333 | 8333.3333
$-land
$-land/unit | 0 | 0 | 0 | 0 | 0
$-permit | 70000 | 70000 | 70000 | 70000 | 50000
$-permit/unit | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 8333.3333
$-sub cost/unit | 114166.6667 | 114166.6667 | 114166.6667 | 114166.6667 | 105833.3333
house ft | 1626 | 1626 | 1626 | 1626 | 1626
$-house/ft | 150 | 150 | 150 | 150 | 130
park ft | 404 | 404 | 404 | 404 | 404
$-park/ft | 70 | 70 | 70 | 70 | 60
$-built/unit | 272180 | 272180 | 272180 | 272180 | 235620
$-cost/unit | 386346.6667 | 386346.6667 | 386346.6667 | 386346.6667 | 341453.3333
$-built tt | 1633080 | 1633080 | 1633080 | 1633080 | 1413720
$-built/ft | 167.3924 | 167.3924 | 167.3924 | 167.3924 | 144.9077
$-cost tt | 2318080 | 2318080 | 2318080 | 2318080 | 2048720
$-cost/ft | 237.6056 | 237.6056 | 237.6056 | 237.6056 | 209.9959
$-market/unit | 528770.6833 | 524193.0417 | 509164.9625 | 458248.4662 | 419550.9083
%-land/market | 21.59% | 21.78% | 22.42% | 24.91% | 25.23%
$-gr-pf-market | 142424.0167 | 137846.375 | 122818.2958 | 71901.7996 | 78097.575
%-gr-pf-market | 26.93% | 26.3% | 24.12% | 15.69% | 18.61%
10% | 429274.0741 | 429274.0741 | 429274.0741 | 429274.0741 | 379392.5926
15% | 454525.4902 | 454525.4902 | 454525.4902 | 454525.4902 | 401709.8039
20% | 482933.3333 | 482933.3333 | 482933.3333 | 482933.3333 | 426816.6667
25% | 515128.8889 | 515128.8889 | 515128.8889 | 515128.8889 | 455271.1111
30% | 551923.8095 | 551923.8095 | 551923.8095 | 551923.8095 | 487790.4762
35% | 594379.4872 | 594379.4872 | 594379.4872 | 594379.4872 | 525312.8205
$-rent/mon | 2391.1765 | 2199.8824 | 2199.8824 | 2199.8824 | 2199.8824
%-rent/cost | 7.427% | 6.833% | 6.833% | 6.833% | 7.731%
tt house ft | 9756 | 9756 | 9756 | 9756 | 9756
$-market/ft | 325.1972 | 322.3819 | 313.1396 | 281.8256 | 258.0264
$-zip-ref/ft | 270 | 270 | 270 | 270 | 270
Note on C1: 809 E Pine St, Compton, CA 90221
Note on C2: DATE EVENT PRICE AGENTS 8/30/2018 Sold $535,000 -- zuser20170313231855204 7/28/2018 Price change $535,000 -7% 7/26/2018 Price change $575,000 -8% 7/19/2018 Listed for sale $625,000 +2.6% 6/7/2018 Listing removed $609,000 -- 5/23/2018 Price change $609,000 -9% 5/17/2018 Price change $669,000 -2.3% 5/4/2018 Price change $685,000 -8.1% 4/25/2018 Price change $745,000 -6.3% 4/17/2018 Listed for sale $795,000 +14.4% 1/10/2018 Listing removed $695,000 -- 10/12/2017 Price change $695,000 -12.6% 10/4/2017 Listed for sale $795,000 +148.4% 3/21/2014 Sold $320,000 -8.6% 7/3/2011 Listing removed $350,000 -5.4% 2/6/2008 Sold $370,000 -39.9% 8/28/2007 Sold $615,343 +107.1% 10/10/2003 Sold $297,118 -- 11/4/2002 Sold $297,118 +6.9% 8/20/2001 Sold $278,000 +68.5% 11/16/1999 Sold $165,000 +10.6% 8/13/1999 Sold $149,130 --
Note on C3: 0.5 acres
Note on C4: max 30 units/acre
Note on C5: 20180727 575000 -> 535000 20180725 625000 -> 575000 20180722 relist -> 625000 THIS IS A LAND DEAL ONLY. SELLER WILL PROVIDE THE FOLLOWING ONLY ! :1-Architectural Design 2-Structural plans 3-Electrical plans 4-Mechanical and Plumbing plans 5-Title24 6 Grading Plan 7-Tentative tract map 8-Landscaping 9-Color Rendering and material & color Board 10-Conditional Approval from planning 11-Conditional Approval from planning for Subdivision PERIOD...... NOTHING MORE. BUYER TO DO THEIR OWN INVESTIGATIONS. MAKE SURE YOU ARE COMFORTABLE WITH COMPTON 20180615 609000 -> 680000
Note on C7: 20190501 50000->80000
Note on C11: 20190501 50000->70000
Note on C16: double 20 x 22
Note on C17: ref 28465/560
Note on C18: 吳老闆最近承接ㄌrevirside 96 unit apart 總造價１２００萬美金 1200/96=12.5
Note on C20: You Will Need to Put Down a Large Down Payment. Typically, 20% is the minimum you need to put down for a construction loan – some lenders require as much as 25% down.
Note on C24: 812 E Pine St UNIT C Compton, CA 90221 1440 sft 340000 20180725 ->358657 20190116 ->369534 20190206 ->371558 20190501 ->452813 20190528 ->449359 20190617 ->450921 20190630 ->454306 20190913 ->464230 20191001 ->468284
Note on C34: 812 E Pine St UNIT A, Compton, CA 90221 1700ft
Note on D1: 809 E Pine St, Compton, CA 90221
Note on D2: DATE EVENT PRICE AGENTS 8/30/2018 Sold $535,000 -- zuser20170313231855204 7/28/2018 Price change $535,000 -7% 7/26/2018 Price change $575,000 -8% 7/19/2018 Listed for sale $625,000 +2.6% 6/7/2018 Listing removed $609,000 -- 5/23/2018 Price change $609,000 -9% 5/17/2018 Price change $669,000 -2.3% 5/4/2018 Price change $685,000 -8.1% 4/25/2018 Price change $745,000 -6.3% 4/17/2018 Listed for sale $795,000 +14.4% 1/10/2018 Listing removed $695,000 -- 10/12/2017 Price change $695,000 -12.6% 10/4/2017 Listed for sale $795,000 +148.4% 3/21/2014 Sold $320,000 -8.6% 7/3/2011 Listing removed $350,000 -5.4% 2/6/2008 Sold $370,000 -39.9% 8/28/2007 Sold $615,343 +107.1% 10/10/2003 Sold $297,118 -- 11/4/2002 Sold $297,118 +6.9% 8/20/2001 Sold $278,000 +68.5% 11/16/1999 Sold $165,000 +10.6% 8/13/1999 Sold $149,130 --
Note on D3: 0.5 acres
Note on D4: max 30 units/acre 0.43 x 30 = 12.89
Note on D5: 20180727 575000 -> 535000 20180725 625000 -> 575000 20180722 relist -> 625000 THIS IS A LAND DEAL ONLY. SELLER WILL PROVIDE THE FOLLOWING ONLY ! :1-Architectural Design 2-Structural plans 3-Electrical plans 4-Mechanical and Plumbing plans 5-Title24 6 Grading Plan 7-Tentative tract map 8-Landscaping 9-Color Rendering and material & color Board 10-Conditional Approval from planning 11-Conditional Approval from planning for Subdivision PERIOD...... NOTHING MORE. BUYER TO DO THEIR OWN INVESTIGATIONS. MAKE SURE YOU ARE COMFORTABLE WITH COMPTON 20180615 609000 -> 680000
Note on D7: 20190501 50000->80000
Note on D11: 20190501 50000->70000
Note on D16: double 20 x 22
Note on D17: ref 28465/560
Note on D18: 吳老闆最近承接ㄌrevirside 96 unit apart 總造價１２００萬美金 1200/96=12.5
Note on D20: You Will Need to Put Down a Large Down Payment. Typically, 20% is the minimum you need to put down for a construction loan – some lenders require as much as 25% down.
Note on D24: 812 E Pine St UNIT C Compton, CA 90221 1440 sft 340000 20180725 ->358657 20190116 ->369534 20190206 ->371558 20190501 ->452813 20190528 ->449359 20190617 ->450921 20190630 ->454306 20190913 ->464230
Note on D34: 812 E Pine St UNIT A, Compton, CA 90221 1700ft
Note on E1: 809 E Pine St, Compton, CA 90221
Note on E2: DATE EVENT PRICE AGENTS 8/30/2018 Sold $535,000 -- zuser20170313231855204 7/28/2018 Price change $535,000 -7% 7/26/2018 Price change $575,000 -8% 7/19/2018 Listed for sale $625,000 +2.6% 6/7/2018 Listing removed $609,000 -- 5/23/2018 Price change $609,000 -9% 5/17/2018 Price change $669,000 -2.3% 5/4/2018 Price change $685,000 -8.1% 4/25/2018 Price change $745,000 -6.3% 4/17/2018 Listed for sale $795,000 +14.4% 1/10/2018 Listing removed $695,000 -- 10/12/2017 Price change $695,000 -12.6% 10/4/2017 Listed for sale $795,000 +148.4% 3/21/2014 Sold $320,000 -8.6% 7/3/2011 Listing removed $350,000 -5.4% 2/6/2008 Sold $370,000 -39.9% 8/28/2007 Sold $615,343 +107.1% 10/10/2003 Sold $297,118 -- 11/4/2002 Sold $297,118 +6.9% 8/20/2001 Sold $278,000 +68.5% 11/16/1999 Sold $165,000 +10.6% 8/13/1999 Sold $149,130 --
Note on E3: 0.5 acres
Note on E4: max 30 units/acre 0.43 x 30 = 12.89
Note on E5: 20180727 575000 -> 535000 20180725 625000 -> 575000 20180722 relist -> 625000 THIS IS A LAND DEAL ONLY. SELLER WILL PROVIDE THE FOLLOWING ONLY ! :1-Architectural Design 2-Structural plans 3-Electrical plans 4-Mechanical and Plumbing plans 5-Title24 6 Grading Plan 7-Tentative tract map 8-Landscaping 9-Color Rendering and material & color Board 10-Conditional Approval from planning 11-Conditional Approval from planning for Subdivision PERIOD...... NOTHING MORE. BUYER TO DO THEIR OWN INVESTIGATIONS. MAKE SURE YOU ARE COMFORTABLE WITH COMPTON 20180615 609000 -> 680000
Note on E7: 20190501 50000->80000
Note on E11: 20190501 50000->70000
Note on E16: double 20 x 22
Note on E17: ref 28465/560
Note on E18: 吳老闆最近承接ㄌrevirside 96 unit apart 總造價１２００萬美金 1200/96=12.5
Note on E20: You Will Need to Put Down a Large Down Payment. Typically, 20% is the minimum you need to put down for a construction loan – some lenders require as much as 25% down.
Note on E24: 812 E Pine St UNIT C Compton, CA 90221 1440 sft 340000 20180725 ->358657 20190116 ->369534 20190206 ->371558 20190501 ->452813 20190528 ->449359 20190617 ->450921 20190630 ->454306 20190913 ->464230
Note on E34: 812 E Pine St UNIT A, Compton, CA 90221 1700ft
Note on F1: 809 E Pine St, Compton, CA 90221
Note on F2: DATE EVENT PRICE AGENTS 8/30/2018 Sold $535,000 -- zuser20170313231855204 7/28/2018 Price change $535,000 -7% 7/26/2018 Price change $575,000 -8% 7/19/2018 Listed for sale $625,000 +2.6% 6/7/2018 Listing removed $609,000 -- 5/23/2018 Price change $609,000 -9% 5/17/2018 Price change $669,000 -2.3% 5/4/2018 Price change $685,000 -8.1% 4/25/2018 Price change $745,000 -6.3% 4/17/2018 Listed for sale $795,000 +14.4% 1/10/2018 Listing removed $695,000 -- 10/12/2017 Price change $695,000 -12.6% 10/4/2017 Listed for sale $795,000 +148.4% 3/21/2014 Sold $320,000 -8.6% 7/3/2011 Listing removed $350,000 -5.4% 2/6/2008 Sold $370,000 -39.9% 8/28/2007 Sold $615,343 +107.1% 10/10/2003 Sold $297,118 -- 11/4/2002 Sold $297,118 +6.9% 8/20/2001 Sold $278,000 +68.5% 11/16/1999 Sold $165,000 +10.6% 8/13/1999 Sold $149,130 --
Note on F3: 0.5 acres
Note on F4: max 30 units/acre 0.43 x 30 = 12.89
Note on F5: 20180727 575000 -> 535000 20180725 625000 -> 575000 20180722 relist -> 625000 THIS IS A LAND DEAL ONLY. SELLER WILL PROVIDE THE FOLLOWING ONLY ! :1-Architectural Design 2-Structural plans 3-Electrical plans 4-Mechanical and Plumbing plans 5-Title24 6 Grading Plan 7-Tentative tract map 8-Landscaping 9-Color Rendering and material & color Board 10-Conditional Approval from planning 11-Conditional Approval from planning for Subdivision PERIOD...... NOTHING MORE. BUYER TO DO THEIR OWN INVESTIGATIONS. MAKE SURE YOU ARE COMFORTABLE WITH COMPTON 20180615 609000 -> 680000
Note on F7: 20190501 50000->80000
Note on F11: 20190501 50000->70000
Note on F16: double 20 x 22
Note on F17: ref 28465/560
Note on F18: 吳老闆最近承接ㄌrevirside 96 unit apart 總造價１２００萬美金 1200/96=12.5
Note on F20: You Will Need to Put Down a Large Down Payment. Typically, 20% is the minimum you need to put down for a construction loan – some lenders require as much as 25% down.
Note on F24: 812 E Pine St UNIT C Compton, CA 90221 1440 sft 20180725 340000->358657 20190116 ->369534 20190206 ->371558 20190501 ->452813 20190528 ->449359 20190617 ->450921
Note on F34: 812 E Pine St UNIT A, Compton, CA 90221 1700ft
Note on G1: 809 E Pine St, Compton, CA 90221
Note on G3: 0.5 acres
Note on G5: 20180727 575000 -> 535000 20180725 625000 -> 575000 20180615 609000 -> 680000 20180722 relist -> 625000 THIS IS A LAND DEAL ONLY. SELLER WILL PROVIDE THE FOLLOWING ONLY ! :1-Architectural Design 2-Structural plans 3-Electrical plans 4-Mechanical and Plumbing plans 5-Title24 6 Grading Plan 7-Tentative tract map 8-Landscaping 9-Color Rendering and material & color Board 10-Conditional Approval from planning 11-Conditional Approval from planning for Subdivision PERIOD...... NOTHING MORE. BUYER TO DO THEIR OWN INVESTIGATIONS. MAKE SURE YOU ARE COMFORTABLE WITH COMPTON
Note on G24: 812 E Pine St UNIT C Compton, CA 90221 20180725 340000->358657 20190116 ->369534 20190206 ->371558
Note on G34: 812 E Pine St UNIT A, Compton, CA 90221 1700ft

## New
工業商用RO | 專用鋁架 | 輪具 | 不鏽鋼架 | 行動式拖架 | 定作款RO
專用RO | 洗車 | 大樓外牆 | RV | 降溫降塵
噴淋 | 滴灌 | 無土栽培 | 有機作物 | 水耕 | 水族
咖啡機 | 飲水機 | 冰箱制冰 | 洗衣機 | 沐浴龍頭 | 定作改裝
自吸水泵 | 遊艇 | 印刷機 | 電鍍機 | 超音波
廣告 | LED | 跑馬燈 | 監控系統 | 人工會慧視別系統
雹子煙 | 大麻 | 美容儀 | 補水機 | 無人機 | 雷射切斷車
包裝泡袋 | 泡袋機 | 出口濾芯 | 智慧冰櫃 | 機場接送APP
寵物用品開發,品牌,新產品設計,專櫃,貿易,寄賣,加盟,中國代購,美國代購
寵物濾芯,浮球,狗盆,給水器,衣物,裝飾品
上門溜狗,看狗,美容,買賣APP