## OPEN
Ref ID | Listed Date | Type | Desc | Attachment | QA Status | QA Comment | Follow Up 0527 | Follow Up 0518 | Follow Up 0512 | Follow Up 0510 | Follow Up 0506
B007 | 2021-05-06 | BUG | title tag on category pages are wrong | QA_B007.png | WILL CHECK |  |  |  | RESOLVED | RESOLVED | RESOLVED
E006 | 2021-05-06 | EXPERIENCE | no "About Us" page; no one knows who Cutie Pet Inc is and do not trust the contact information or the company because it's unrelated to the website |  | WILL CHECK |  |  |  | will add |  | will add
E029 | 2021-05-08 | EXPERIENCE | on search page, when adding item to wish list, page scrolls to the top which interrupts shopping |  | WILL CHECK |  |  |  | user can't see responsed msg if not scroll
E034 | 2021-05-12 | EXPERIENCE | 不太清楚contact seller 跟 trader 的不同 是不是要把它們combine起來? |  | WILL CHECK |  |  |  | seller for retail, trader for wholesale
B014 | 2021-05-14 | BUG | entering wg-1.com the page shows I'm not logged in even though I already logged in, clicking anywhere else on the site will show logged in. willgetone.com do not have the same issue, see attached image | B014.png |  |  | RESOLVED - fixed | will check the redirct
E035 | 2021-05-14 | EXPERIENCE | "View Depot" and "View Cart" button should be at the top so user doesn't have to scroll all the way to the bottom of the item list |  | WILL CHECK | 我已經checkout了 depot裡沒貨 現在不能check |  | RESOLVED - changed
E039 | 2021-05-18 | EXPERIENCE | * Specify any regions part of USA that WG1 will not deliver to, e.g. "(except for Puerto Rico, Hawaii, Guam)" | feedback 2021-05-17.txt | WILL CHECK |  |  | RESOLVED -added (48 states only)
E040 | 2021-05-18 | EXPERIENCE | Please add the same excluded regions to the Arrival Notice. | feedback 2021-05-17.txt | WILL CHECK |  |  | don't know where to add
L018 | 2021-05-18 | LANGUAGE | Contact Us page * Add disclaimer "Cutie Pet Inc. is our parent company, based in the USA." * Please remove the phone number. Customer will want to call a number when they see any problem and they will be frustrated when no one will pick up the phone. | feedback 2021-05-17.txt | WILL CHECK |  |  | RESOLVED - changed
L020 | 2021-05-18 | LANGUAGE | Arrival Notice revised | Arrival Notice (edited 2021-05-17).txt | WILL CHECK |  |  | RESOLVED - changed
B015 | 2021-05-23 | BUG | Seeing this in thumbnail: "Warning: Undefined array key "product_id" in /var/www/html/..." | B015.jpg |  |  | 無法再出現 error, 查不出原因,可能是那時正在改程式
B016 | 2021-05-23 | BUG | already logged in, depot 是空的時候顯示要求 login | B016.jpg |  |  | RESOLVED - fixed
B017 | 2021-05-23 | BUG | same as B016 | B017.jpg |  |  | RESOLVED - fixed
L023 | 2021-05-23 | LANGUAGE | 東西寄出的message要改 請把所有的 * 改用 <ul> Your shipment request has been submitted! Thanks for shopping with willgetone.com! What's next? * We will send you an email with further confirmation details once we have shipped out your package. * You can view your order in the Order History page. * Please do not hesitate to contact us if you have any questions. | L023.jpg |  |  | RESOLVED - changed
L024 | 2021-05-23 | LANGUAGE | Post Code 改 Postal Code |  |  |  | RESOLVED - changed
L025 | 2021-05-23 | LANGUAGE | Postal Code should be required | L025.jpg |  |  | RESOLVED - fixed
E042 | 2021-05-23 | EXPERIENCE | cannot delete or edit address, need to retype everything. 打錯的話很困擾 | E042.jpg |  |  | 請看備註
E043 | 2021-05-23 | EXPERIENCE | warning message 的 x 歪歪的 | E043.jpg |  |  | 請問 error message 是在哪一個步驟時出現, 圖片上看不出來
E044 | 2021-05-23 | EXPERIENCE | 客人看了會以為要再付一次item price | E044.jpg |  |  | RESOLVED - changed into Paid 最下方面的 total 也不包含貨品的價格
E045 | 2021-05-23 | EXPERIENCE | 目前shipping只有一個選擇嗎 | E045.jpg |  |  | 因為剛好這一件的總重超過了其他物流的上限,所以只剩一種
E046 | 2021-05-23 | EXPERIENCE | 請remove "Are you sure..." 把full message改成 Please select at least one item to qualify for shipping. and remove "Cancel" button | E046.jpg |  |  | RESOLVED - changed
B018 | 2021-05-23 | BUG | 在沒有select any item情況下 上一次的total shipping還在 | B018.jpg |  |  | RESOLVED - fixed
E047 | 2021-05-23 | EXPERIENCE | "Arrived in Depot" 文字擠在一起 | E047.jpg |  |  | RESOLVED - fixed
E048 | 2021-05-25 | EXPERIENCE | 收到兩封shipped out notice? 第二封有 "You may receive the products within 10~20 days." |  |  |  | 不好意思,因為正好在測試,所以加了天數,再補了第二封
L026 | 2021-05-25 | LANGUAGE | change email subject: willgetone.com - Order No. <order_no> Has Been Shipped change email content: Hi <customer_name>, Your willgetone.com order has been shipped out from our Transship Depot in China and is on your way! We estimate you may receive the package within <estimated_days> days. To track your package, please visit this link and enter the tracking number provided: <tracking_link> Package Tracking Number: <tracking_number> <items> Thank you for choosing willgetone.com for your wholesale shopping needs! Please feel free to reply to this e-mail with any questions. |  |  |  | RESOLVED - changed
E049 | 2021-05-25 | EXPERIENCE | 48 states 的話要改圖, see attachment | box_globe_003.png |  |  | RESOLVED - changed
L027 | 2021-05-25 | LANGUAGE | Transship Process page 請把所有的1) 2) 3) 改用 <ol> 把 * 改用 <ul> 順便把 "willgetone.com offers a flexible wholesale shopping experience" 的句終符號改成":" | L027.png |  |  | RESOLVED - changed
L028 | 2021-05-25 | LANGUAGE | About Us page 請把所有的1) 2) 3) 改用 <ol> 還有 How does willgetone.com work? 改跟L027一致 | L028.png |  |  | RESOLVED - changed
Note on H12: https://www.willgetone.com/index.php?route=product/product&product_id=13582&search=cute&page=3
Note on H18: 1.) 正常修改地址要進 My Account -> Modify your address book entries 2.) 因為在第一次 cart checkout 時,為了不讓客人誤會所以故意不用填地址, 系統先建了一個假的 default 假地址, 在第二次 depot checkout 時,才強迫客人填完整地址

## DONE
Ref ID | Listed Date | Type | Desc | Attachment | QA Status | QA Comment | Follow Up 0518 | Follow Up 0512 | Follow Up 0510 | Follow Up 0506
B001 | 2021-05-06 | BUG | item preview thumbnails are incorrect |  | RESOLVED | 好像沒有thumbnail了 |  | 小螢幕時(手機)會把thumbnail去掉 |  | don't know which incorrect
B002 | 2021-05-06 | BUG | must type "www.", otherwise website will not load |  | RESOLVED |  |  | RESOLVED | RESOLVED | RESOLVED
B003 | 2021-05-06 | BUG | "Warning: fsockopen(): Unable to connect to max.wg-1.com:26 (Connection refused) in /var/www/html/system/library/mail/smtp.php on line 87" |  | RESOLVED |  |  | RESOLVED | RESOLVED | RESOLVED
B004 | 2021-05-06 | BUG | "translate image" takes too long / might not be working |  | RESOLVED |  |  | RESOLVED |  | Test OK pls check again
B005 | 2021-05-06 | BUG | some icons are not loaded on wg-1 domain (search, arrow) |  | RESOLVED |  |  | RESOLVED | RESOLVED | RESOLVED
B006 | 2021-05-06 | BUG | "Recently Viewed" displays items not visited yet |  | WON'T DO | 你的意思是 沒有log in的user看到的是random items對嗎? 那是不是不應該說"recently viewed" 這樣不符合situation |  | 所有沒有log in的user看到的都合併在一起 customer_id=0, 所以會看到其他的人記錄, 這樣也可以給新人參考 | RESOLVED | all un-login users (customer_id=0) viewed mixed
B008 | 2021-05-08 | BUG | red heart from E015 should not display when adding to wish list before logging in |  | RESOLVED |  |  | RESOLVED - fixed
B009 | 2021-05-08 | BUG | in search page, red heart from E015 do not display |  | WON'T DO |  |  | hard to fix, too many to fixed
B010 | 2021-05-08 | BUG | 有時候會看到 "SyntaxError: JSON.parse: unexpected character at line 1 column 1 of the JSON data OK <b>Warning</b>: unlink(/var/www/storage/cache/cache.catalog.language.1620516351): No such file or directory in <b>/var/www/html/system/library/cache/file.php</b> on line <b>68</b>{"dv_eub":{"code":"dv_eub","title":"Standard Shipping (via USPS)","quote":{"dv_eub":{"code":"dv_eub.dv_eub","title":"Standard Shipping (via USPS)","cost":-1,"typecost":{"allcart":-1,"selectcart":-1,"alldepot":-1,"selectdepot":-1,"depotcart":-1,"depotselcart":-1,"standard2k":33.39,"productweight":6.6,"max":33.39},"typeweight":{"standard2k":2000,"productweight":36,"max":2000},"tax_class_id":null,"text":"$-1.00"}},"sort_order":"3","error":false},"dv_yw01":{"code":"dv_yw01","title":"Economy Shipping","quote":{"dv_yw01":{"code":"dv_yw01.dv_yw01","title":"Economy Shipping","cost":-1,"typecost":{"allcart":-1,"selectcart":-1,"alldepot":-1,"selectdepot":-1,"depotcart":-1,"depotselcart":-1,"standard2k":24.92,"productweight":3.46,"max":354.33},"typeweight":{"standard2k":2000,"productweight":36,"max":30000},"tax_class_id":null,"text":"$-1.00"}},"sort_order":"3","error":false}}" |  | WON'T DO |  |  | 找不出真正原因,已試改了一部分, 如果有再出現請通知我
B011 | 2021-05-10 | BUG | 有時候 log in 的時候會看到 "Warning: Undefined array key "cartselect" in /var/www/html/system/library/cart/cart.php on line 31" at top of page |  | RESOLVED |  |  | RESOLVED - fixed
B012 | 2021-05-14 | BUG | on mobile phone, logged in, when I clicked on "Bestsellers" or "Dollar Sale" categories, see attached image |  | RESOLVED | 2021-05-16 checked, issue is gone
B013 | 2021-05-14 | BUG | wg-1 icons are missing again (B005) |  | RESOLVED |  | RESOLVED - fixed
E001 | 2021-05-06 | EXPERIENCE | no refresh feature to get new captcha |  | RESOLVED |  |  | RESOLVED | RESOLVED | will change into google reCaptcha
E002 | 2021-05-06 | EXPERIENCE | "recently viewed" displays same item from different computers (IP address?) |  | WON'T DO | 我的意思是 在沒有log in的情況下 同一個家裡所有的device 看到的"recently viewed" items都一致 是不是因為用了IP address來做caching? |  | 所有沒有log in的user看到的都合併在一起 customer_id=0, 所以會看到其他的人記錄, 這樣也可以給新人參考 | RESOLVED | all un-login users (customer_id=0) viewed mixed
E003 | 2021-05-06 | EXPERIENCE | default 15 items per page is too few, especially on mobile phone |  | RESOLVED |  |  | RESOLVED | RESOLVED | RESOLVED
E004 | 2021-05-06 | EXPERIENCE | cannot browse or see "more items by same seller" |  | WON'T DO |  |  | WON'T DO | RESOLVED | source data no seller infor to get same seller
E005 | 2021-05-06 | EXPERIENCE | no explanation why Captcha is required |  | WON'T DO |  |  | WON'T DO | RESOLVED | will change into google reCaptcha
E007 | 2021-05-06 | EXPERIENCE | customers might not want to see 18+ and political content on front page |  | WON'T DO |  |  | WON'T DO |  | front page=home page?
E008 | 2021-05-06 | EXPERIENCE | no filter (18+ content) during shopping |  | WON'T DO |  |  | WON'T DO | RESOLVED | hard to do and ebay, amazon either
E009 | 2021-05-06 | EXPERIENCE | no endless scrolling feature |  | WON'T DO |  |  | Hard to do, changed similar item count 20 into 50 |  | will add
E010 | 2021-05-06 | EXPERIENCE | item order is shuffled if page refreshes |  | RESOLVED |  |  | RESOLVED | RESOLVED | item order generated by SQL RAND() per page
E011 | 2021-05-06 | EXPERIENCE | seeing repeated items on different pages |  | RESOLVED |  |  | RESOLVED | RESOLVED | item order generated by SQL RAND() per page
E012 | 2021-05-06 | EXPERIENCE | no "peek password" during login or password change |  | RESOLVED |  |  | RESOLVED | RESOLVED | RESOLVED
E013 | 2021-05-06 | EXPERIENCE | "Pricacy Policy" page has ro-sales email, customer would be confused |  | RESOLVED |  |  | RESOLVED | RESOLVED | RESOLVED
E014 | 2021-05-06 | EXPERIENCE | "Transfer process" page step numbers do not match with image |  | RESOLVED | 那還是把圖片remove掉好了? |  | RESOLVED - change number into icon | RESOLVED | 1~4,V is status, not step in Transfer process page
E015 | 2021-05-06 | EXPERIENCE | no visual marking to show item is already in wishlist |  | RESOLVED |  |  | RESOLVED | RESOLVED | RESOLVED
E016 | 2021-05-06 | EXPERIENCE | product image fade-in during scrolling is slow and annoying |  | RESOLVED | 從台灣沒問題 我的意思是 每次要load 圖片都會緩慢的淡入 看的有點不舒服 |  | 因為 server 在台灣, 網速可能不夠快, fade in changed 3s into 0.5s |  | How offen? or always? The image server at Taipei Co.
E017 | 2021-05-06 | EXPERIENCE | search bar is not always visible |  | WON'T DO | 沒事 只是說很多網站的 search bar 就算page scroll down 隨時也都看得到 你可以參考 |  | hard to Do |  | Which page? What situation?
E018 | 2021-05-06 | EXPERIENCE | logo is not always visible (to go to home page) |  | WON'T DO | 跟E017 意思一樣 只是指logo |  | hard to Do |  | Which page? What situation?
E019 | 2021-05-06 | EXPERIENCE | logo is too big on mobile phone and takes up space |  | RESOLVED |  |  | RESOLVED -> scaling 65% | RESOLVED -> scaling 65% | RESOLVED -> scaling 65%
E020 | 2021-05-06 | EXPERIENCE | when page needs more room, logo can switch to box only instead of including domain names |  | WON'T DO | 沒事 只是建議 logo圖片可以縮小成只有紙箱人(沒有網址)來省空間 因為mobile phone的螢幕比較小 看了現在的葉面其實目前還可以 |  | WON'T DO |  | Which page?
E021 | 2021-05-06 | EXPERIENCE | item loading animation is weird (black color gives high contrast) |  | RESOLVED |  |  | RESOLVED -> logo color | RESOLVED -> logo color | RESOLVED -> logo color
E022 | 2021-05-06 | EXPERIENCE | "x" button is misaligned for "You must login... wishlist" message |  | RESOLVED |  |  | RESOLVED | RESOLVED | RESOLVED
E023 | 2021-05-06 | EXPERIENCE | using a check mark icon for "You must login... wishlist" message is a little weird |  | RESOLVED |  |  | RESOLVED -> exclamation | RESOLVED -> exclamation | RESOLVED -> exclamation
E024 | 2021-05-06 | EXPERIENCE | wishlist item count added before login is still deployed at the top |  | RESOLVED |  |  | RESOLVED | RESOLVED | RESOLVED
E025 | 2021-05-08 | EXPERIENCE | "Contact seller" prompt window has no cancel button |  | RESOLVED |  |  | RESOLVED - added
E026 | 2021-05-08 | EXPERIENCE | on item page, add more space above "Similar Products", 請看附件圖片QA_E026 |  | RESOLVED |  |  | RESOLVED - added
E027 | 2021-05-08 | EXPERIENCE | opposite of E023: a check box icon should be used for added item to wish list |  | RESOLVED |  |  | RESOLVED - changed
E028 | 2021-05-08 | EXPERIENCE | search criteria: if I type "table", I get results for "comfortable". 好像不太對 |  | WON'T DO |  |  | 這是SQL的限制, 不知道要如何解決, 不過這樣反而給客人更多的結果, 所以應該還OK
E030 | 2021-05-08 | EXPERIENCE | allow removing from wish list when clicking on the heart, tool tip can be updated to say "Remove from wish list" |  | WON'T DO |  |  | 希望客人不要太容易取消
E031 | 2021-05-11 | EXPERIENCE | "Unit Price" in Wish List looks like higher amount than item, this can be confusing |  | RESOLVED |  |  | RESOLVED - fixed
E032 | 2021-05-12 | EXPERIENCE | PayPal page says "Cancel and return to Cutie Pet Inc", is the company correct? |  | RESOLVED |  |  | 是用 Cutie Pet Inc 去申請收款的
E033 | 2021-05-12 | EXPERIENCE | E012的新feature 可以加在 sign up page嗎? |  | RESOLVED |  |  | RESOLVED - added
E036 | 2021-05-16 | EXPERIENCE | Arrival Notice: 358是什麼 |  | RESOLVED |  | RESOLVED - changed into Arrival Notice of Order No: 358
E037 | 2021-05-16 | EXPERIENCE | suggestion, 是不是要給Depot取一個名字 讓它正式一點 除非是不同個的地點來當Depot 像一些partner一起合作? |  | RESOLVED | 看到了 叫Transship Depot 以後記得要用大寫來稱呼它 | RESOLVED - changed
E038 | 2021-05-16 | EXPERIENCE | "Warning: You must agree to the Privacy Policy!" 應該把"warning"除掉 |  | RESOLVED |  | RESOLVED - changed
E041 | 2021-05-18 | EXPERIENCE | Main Page * Provide a link to full Transship Process page near the top banner ("shop like a wholesaler in 2 steps!"). + "Click for more details". Maybe you can allow customer to click on the image to go directly to the page. | feedback 2021-05-17.txt | RESOLVED |  | RESOLVED - changed
L001 | 2021-05-06 | LANGUAGE | during translate image, text are "Cencel" "loading", they should be "Cancel" and "Loading" |  | RESOLVED | see L014 |  | RESOLVED | RESOLVED | RESOLVED
L002 | 2021-05-06 | LANGUAGE | "Contact Us" -> "Enquiry" is UK English, American English should be "Inquiry" |  | RESOLVED |  |  | RESOLVED | RESOLVED | RESOLVED
L003 | 2021-05-06 | LANGUAGE | "You must login or create an account to save ... to your wishlist!", "login" is noun, use "log in" for verb. Also the item name is too long, can replace message with "You must log in or create an account to save this item to your wishlist!" |  | RESOLVED |  |  | RESOLVED | RESOLVED | RESOLVED
L004 | 2021-05-08 | LANGUAGE | "Trader" prompt window has "Cencel" misspelling |  | RESOLVED |  |  | RESOLVED - changed
L005 | 2021-05-08 | LANGUAGE | on item page, use American English "Color" instead of UK English "colour", also capitalize first letter to be consistent with "Qty" 如果是seller自己寫的就算了 |  | WON'T DO |  |  | all option name translated by google, too many item to change
L006 | 2021-05-08 | LANGUAGE | "Qty" could be spelled out fully "Quantity" |  | RESOLVED |  |  | RESOLVED - changed
L007 | 2021-05-08 | LANGUAGE | "Top Category" should be pluralized to "Top Categories" |  | RESOLVED |  |  | RESOLVED - changed
L008 | 2021-05-08 | LANGUAGE | "Women's Long-sleeved Top" should be pluralized to "Women's Long-sleeved Tops" |  | RESOLVED |  |  | RESOLVED - changed
L009 | 2021-05-08 | LANGUAGE | "Women's Coat" should be pluralized to "Women's Coats" |  | RESOLVED |  |  | RESOLVED - changed
L010 | 2021-05-08 | LANGUAGE | "Women's Short-sleeved Top" should be pluralized to "Women's Short-sleeved Tops" |  | RESOLVED |  |  | RESOLVED - changed
L011 | 2021-05-08 | LANGUAGE | "Women's Lace Top" should be pluralized to "Women's Lace Tops" |  | RESOLVED |  |  | RESOLVED - changed
L012 | 2021-05-08 | LANGUAGE | "Key Chain" should be pluralized to "Key Chains" |  | RESOLVED |  |  | RESOLVED - changed
L013 | 2021-05-08 | LANGUAGE | "Privacy Policy" page, there should be a space after "Email:" |  | RESOLVED |  |  | RESOLVED - changed
L014 | 2021-05-12 | LANGUAGE | "Translate image" window button incorrectly says "Cencel", should be "Cancel" |  | RESOLVED |  |  | RESOLVED - changed
L015 | 2021-05-14 | LANGUAGE | 改成這個比較順 "Selected Total Weight", "Selected Total Shipping", "Depot Total Weight", "Depot Total Shipping", see attached image |  | RESOLVED |  | Main Page
L016 | 2021-05-16 | LANGUAGE | Change "Logout" to verb form "Log out" |  | RESOLVED |  | RESOLVED - changed
L017 | 2021-05-18 | LANGUAGE | See Transship Process mockup edit.png (1)(2) Transship process should be capitalized to "Transship Process" (3) Shop from various sellers in China -> Goods arrive at our Transship Depot -> We'll inspect and combine all goods into one package -> Select shipping option -> Receive goods Transship Process page revided | feedback 2021-05-17.txt | RESOLVED |  | RESOLVED - changed
L019 | 2021-05-18 | LANGUAGE | Site Footer * Change "Returns" to "Order Return Form", also apply this to the page's title. * Change "Transship process" to "Transship Process" | feedback 2021-05-17.txt | RESOLVED |  | RESOLVED - changed
L021 | 2021-05-18 | LANGUAGE | Transship Process page revised | Transship Process (edited 2021-05-17).txt | RESOLVED |  | RESOLVED - changed
L022 | 2021-05-18 | LANGUAGE | About Us page revised | About Us (edited 2021-05-17).txt | RESOLVED |  | RESOLVED - changed
S001 | 2021-05-06 | SECURITY | "connection is not secure" message next to website URL |  | RESOLVED | 有用https了 |  | RESOLVED |  | don't know what the mean
S002 | 2021-05-06 | SECURITY | signup page do not have terms and privacy agreement acknowledgement |  | RESOLVED |  |  | RESOLVED | RESOLVED | will add
S003 | 2021-05-12 | SECURITY | 如果用www.willgetone.com, willgetone.com, wg-1.com, www.wg-1.com進入網站, S001的問題又出現, 沒用https. 是不是要做個redirect到https? |  | RESOLVED |  |  | S001是 browser 提示的, 客人用 http 進入後, 再進入所有的下一頁都會轉到 https, 會試一下直接 redirect

## VALIDATIONS
Type | QA Status
EXPERIENCE | WON'T DO
BUG | WILL CHECK
LANGUAGE | RESOLVED
SECURITY